EDDIEfication SOP (Productionizing an ML Use Case)

1. What is EDDIEfication?

EDDIEfication is the process of converting a machine learning use case into a fully operational solution on the EDDIE platform.

It ensures the pipeline runs automatically, data flows correctly, and outputs are available for business use.

The process includes development, validation, and deployment across environments.

It also ensures governance through access control, approvals, and integrations.

2. End-to-End Overview

- Dev → Build, refactor, integrate, and test

- Stage → Validate integrations and approvals

- Prod → Deploy and operationalize

3. Phase 1: Dev (Development & Testing)

Step 1: Perform refactorization of code (8 days)

Step 2: Onboard the use case into EDDIE (3 days)

Step 3: Raise access requests for required AD groups (3 days)

Step 4: Test pipeline on workbench (3 days)

Step 5: Set up EDNA toll gate ingestion (3 days)

Step 6: Raise EDNA consumption ticket (3 days)

Step 7: Create ticket for MFT process (3 days)

Step 8: Perform MFT testing (3 days)

Step 9: Raise CR for data (3 days)

Step 10: Push sales rep data to EDNA (3 days)

Step 11: Repeat push for validation (3 days)

Step 12: Create output tables (3 days)

Step 13: Enable dataset consumption (3 days)

Step 14: Create VW datasets (3 days)

Step 15: Provide service account access (3 days)

Step 16: Validate access (3 days)

Step 17: Validate modules (4 days)

Step 18: Update config file (4 days)

Step 19: Dockerization (5 days)

Step 20: Trigger pipeline (4 days)

Step 21: Fix issues (4 days)

Step 22: Integrate Vertex AI (4 days)

Step 23: Push code to GitHub (4 days)

Step 24: Fix issues again (4 days)

Step 25: Validate integration (4 days)

Step 26: Integrate Airflow DAG (4 days)

4. Phase 2: Stage (Validation)

Step 27: Send onboarding email (4 days)

Step 28: Coordinate with EDDIE team (3 days)

Step 29: Provide access (3 days)

Step 30-32: Perform integration (3 days each)

Step 33: Prepare CR documents (3 days)

Step 34: Conduct CR review (3 days)

Step 35: Activate CR (3 days)

5. Phase 3: Prod (Deployment)

Step 36: Send onboarding email (3 days)

Step 37: Coordinate with EDDIE team (3 days)

Step 38: Provide access (3 days)

Step 39-41: Perform integration (3 days each)

6. Final Step: Communication

Subject: EDDIEfication Successful – [Use Case Name]

Body:

- Dev, Stage, and Prod completed

- Use case live

- All systems functioning

- Notes if any