## Timeline EDDIE
Activity | Description | Owner | ETA | time axis 2025-11-13 to 2026-03-22
Refactorization | Optimization of 10 python code modules | Praven/Sagar |  | 2025-11-13: X; 2025-11-24: Freeze Period; 2025-12-22: Freeze Period; 2025-12-29: Freeze Period; 2026-01-05: Freeze Period; 2026-03-20: Planned Deadline
Onboarding the use case ITA - EDDIE | Update questionnaire and submit | Praven/Sagar | bar: 2025-11-13 to 2025-11-14; 2025-11-17 to 2025-11-19
Access requests for required AD groups | Raise access requests for Non prod and prod AD groups | Praven | bar: 2025-11-20 to 2025-11-21
Test pipeline on workbench | Move all the 10 code modules and test it onworkbench | Praven | bar: 2025-11-20 to 2025-11-21; 2025-12-01 to 2025-12-02
EDNA toll gate ingestion - Rep level data | Submit ticket for EDnA tollgate ingestion team for creation of D0 table for sales rep data | Praven/Nikhil | bar: 2025-12-01 to 2025-12-05; 2025-12-08 to 2025-12-12
EDnA Consumption ticket | Submit ticket for EDnA tollgate consumption team for creation of VI2 table for sales rep data | Praven/Nikhil | bar: 2025-12-11 to 2025-12-12; 2025-12-15 to 2025-12-19
Ticket for MFT Process | Submit ticket for MFT process in order to perform monthly refresh of sales rep data from shared path | Praven/Sagar/Nikhil | bar: 2026-01-12
MFT testing | Ingestion team to test the MFT process in Dev and move the data to stage | Kiran Kondebettu | bar: 2026-01-13 to 2026-01-16; 2026-01-19
CR for data | Update CR for ship to level data and sales rep level data | Praven/Nikhil | bar: 2026-01-19 to 2026-01-23
Push sales rep data to edna-pr | VI2 for ship to level data & sales rep data should be pushed from edna-np to edna-stage | Pooja/Tharang/Hariom | bar: 2026-01-27 to 2026-01-30; 2026-02-02 to 2026-02-06
Push sales rep data to edna-pr | VI2 for ship to level data & sales rep data should be pushed from edna-stage to edna-pr to access it from Vertex AI | Pooja/Tharang/Hariom | bar: 2026-02-09 to 2026-02-13; 2026-02-16 to 2026-02-18
Output table creation in edna-edd-pr | D2 table creation for outputing model results into edna-edd-pr. From here the data will be refreshed in the dashboard | Praven/Jayesh | bar: 2026-02-19
EDnA Tollgate consumption for creation of VW, VI2 and D2 empty datasets | Coordinate with Jayesh/Vashnavi for creation of 2 view datasets for original 2 EDNA VI2 datasets | Jayesh/Vaishnavi/Nikhil | bar: 2026-02-19
VW images to be created from the original two source D2 tables | Coordinate with Jayesh/Vashnavi for creation of view images for 2 EDNA VI2 tables and this can be done in freeze period or not | Jayesh/Vaishnavi/Nikhil/Irfan | bar: 2026-02-19 to 2026-02-20; 2026-02-23 to 2026-02-24
Service account acces to both inputs inside edna-data-pr | Raise service now ticket for eddie dev service account to get read access for VW (sales rep data) | Sagar | bar: 2026-02-25
Check VW access | To check whether we are able to read from the view tables | Praven/Sagar | bar: 2026-02-25 to 2026-02-26
DEV ENVIRONMENT | bar: 2026-02-25 to 2026-02-26
Validation of Modules | Validation of refactored modules in workbench | Praven/Sagar | 2026-02-27 | bar: 2026-02-27
Update config file | Update input data sources must read from edna-data-pr | Praven | 2026-02-27 | bar: 2026-02-27
Dockerization image and create requirements.txt | Create a docker file and manually push the image to harbor | Praven/Sagar | 2026-03-02 | bar: 2025-11-23; 2026-03-02
Trigger Pipeline | Trigger the pipeline from workbench using AIRFLOW template | Praven | 2026-03-02 | bar: 2026-03-02
Fix refactorized code for errors in development environment (Manual Trigger) | Debug if any errors occur | Praven/Sagar | 2026-03-02 | bar: 2026-03-04
Vertex AI integration | Nitro DX setup | Jayesh | 2026-03-04 | bar: 2026-03-04
Push codes to GitHub | Push final code to GithHub | Praven/Sagar | 2026-03-04 | bar: 2026-03-04
Fix refactorized code for errors in development environment (Manual Trigger) | Debug if any errors occur | Praven/Sagar | 2026-03-05 | bar: 2026-03-05
Vertex AI integration | Create Airflow DAG and upload to Airflow GCS bucket | Jayesh | 2026-03-05 | bar: 2026-03-05
AIRFLOW DAG TO EDDIE | Trigger the entire Nitro DX pipeline using Airflow DAG (In Dev) | Praven/Jayesh | 2026-03-05 | bar: 2026-03-05
STAGE ENVIRONMENT
Send an e-mail to EDDIE team to onboard on stage | Send mail to onboard usecase to stage | Praven | 2026-03-05 | bar: 2026-03-05
EDDIE TEAM | Onboarding the project to stage | Jayesh | 2026-03-06
Service account acces (Stage) to both inputs inside edna-data-pr | Raise service now ticket for eddie stage service account to get read access for VW (for both input data sources) | Praven/Sagar/Sunil/EDnA Team/Jas | 2026-03-10
Integration on stage environment | Push the updated code to GitHub for Stage | Sagar/Praven | 2026-03-10
Integration on stage environment | Modify Config.yaml, Set up Airflow DAG for Stage and Jira card approval from EDDIE team | Praven/Jayesh | 2026-03-10
Integration on stage environment | Ensure code is running without issues in MLOps Stage pipeline | Praven/Sagar/Jayesh/Nikhil | 2026-03-10
Documents for active CR | Testing documents, T Minus 1 document, Approval email from Irfan | Praven/Pooja/Irfan | 2026-03-10
CR Review | The Board Review Meeting For CR Approval | Pooja | 2026-03-10
Active CR | CR ready for migrating the usecase to production (Provide the approval by 03/11/2026) | Pooja/Shivam/Anoop | 2026-03-16
Prod Environment
Send an e-mail to EDDIE team to onboard on prod | Send an e-mail to EDDIE team to onboard usecase to prod | Jayesh | 2026-03-12
EDDIE TEAM | Onboarding the project to prod | Jayesh | 2026-03-16
Service account acces to both inputs inside edna-data-pr | Raise service now ticket for eddie prod service account to get read access for VW (for both input data sources) | Praven/Sagar | 2026-03-18
Integration on stage environment | Push the updated code to GitHub for prod | Praven | 2026-03-18
Integration on stage environment | Modify Config.yaml, Set up Airflow DAG for prod and Jira card approval from EDDIE team | Praven/Jayesh | 2026-03-18
Integration on stage environment | Ensure code is running without issues in MLOps prod pipeline | Praven/Sagar/Jayesh/Nikhil | 2026-03-18
Note on P27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependency on Eddie team

## Sheet1
S.No | Activity | Description
1 | Refactorization | Optimization of 10 python code modules
2 | Onboarding the use case ITA - EDDIE | Update questionnaire and submit
3 | Access requests for required AD groups | Raise access requests for Non prod and prod AD groups
4 | Test pipeline on workbench | Move all the 10 code modules and test it onworkbench
5 | EDNA toll gate ingestion - Rep level data | Submit ticket for EDnA tollgate ingestion team for creation of D0 table for sales rep data
6 | EDnA Consumption ticket | Submit ticket for EDnA tollgate consumption team for creation of VI2 table for sales rep data
7 | Ticket for MFT Process | Submit ticket for MFT process in order to perform monthly refresh of sales rep data from shared path
8 | MFT testing | Ingestion team to test the MFT process in Dev and move the data to stage
9 | CR for data | Update CR for ship to level data and sales rep level data
10 | Push sales rep data to edna-pr | VI2 for ship to level data & sales rep data should be pushed from edna-np to edna-stage
11 | Push sales rep data to edna-pr | VI2 for ship to level data & sales rep data should be pushed from edna-stage to edna-pr to access it from Vertex AI
12 | Output table creation in edna-edd-pr | D2 table creation for outputing model results into edna-edd-pr. From here the data will be refreshed in the dashboard
13 | EDnA Tollgate consumption for creation of VW, VI2 and D2 empty datasets | Coordinate with Jayesh/Vashnavi for creation of 2 view datasets for original 2 EDNA VI2 datasets
14 | VW images to be created from the original two source D2 tables | Coordinate with Jayesh/Vashnavi for creation of view images for 2 EDNA VI2 tables and this can be done in freeze period or not
15 | Service account acces to both inputs inside edna-data-pr | Raise service now ticket for eddie dev service account to get read access for VW (sales rep data)
16 | Check VW access | To check whether we are able to read from the view tables
DEV ENVIRONMENT
18 | Validation of Modules | Validation of refactored modules in workbench
19 | Update config file | Update input data sources must read from edna-data-pr
20 | Dockerization image and create requirements.txt | Create a docker file and manually push the image to harbor
21 | Trigger Pipeline | Trigger the pipeline from workbench using AIRFLOW template
22 | Fix refactorized code for errors in development environment (Manual Trigger) | Debug if any errors occur
23 | Vertex AI integration | Nitro DX setup
24 | Push codes to GitHub | Push final code to GithHub
25 | Fix refactorized code for errors in development environment (Manual Trigger) | Debug if any errors occur
26 | Vertex AI integration | Create Airflow DAG and upload to Airflow GCS bucket
27 | AIRFLOW DAG TO EDDIE | Trigger the entire Nitro DX pipeline using Airflow DAG (In Dev)
28 | STAGE ENVIRONMENT
29 | Send an e-mail to EDDIE team to onboard on stage | Send mail to onboard usecase to stage
30 | EDDIE TEAM | Onboarding the project to stage
31 | Service account acces (Stage) to both inputs inside edna-data-pr | Raise service now ticket for eddie stage service account to get read access for VW (for both input data sources)
32 | Integration on stage environment | Push the updated code to GitHub for Stage
33 | Integration on stage environment | Modify Config.yaml, Set up Airflow DAG for Stage and Jira card approval from EDDIE team
34 | Integration on stage environment | Ensure code is running without issues in MLOps Stage pipeline
35 | Documents for active CR | Testing documents, T Minus 1 document, Approval email from Irfan
36 | CR Review | The Board Review Meeting For CR Approval
37 | Active CR | CR ready for migrating the usecase to production (Provide the approval by 03/11/2026)
38 | Prod Environment
39 | Send an e-mail to EDDIE team to onboard on prod | Send an e-mail to EDDIE team to onboard usecase to prod
40 | EDDIE TEAM | Onboarding the project to prod
41 | Service account acces to both inputs inside edna-data-pr | Raise service now ticket for eddie prod service account to get read access for VW (for both input data sources)
42 | Integration on stage environment | Push the updated code to GitHub for prod
43 | Integration on stage environment | Modify Config.yaml, Set up Airflow DAG for prod and Jira card approval from EDDIE team
44 | Integration on stage environment | Ensure code is running without issues in MLOps prod pipeline

## Dev
S.No | Activity | Description | Business Days To Complete
1 | Refactorization | Optimization of python code modules | 7
2 | Onboarding the use case - EDDIE (Dev Environment) | Update questionnaire and submit | 1 (We can do this with step 1)
3 | Onboarding to Dev confirmation | Confirmation mail from EDDIE team | 1
4 | Access requests for required AD groups | Raise access requests for Non prod and prod AD groups for workbench access in GCP | 1
5 | GitHub Repository Creation | Create the GitHub repository for the EDDIE use case based on MLOps template provide by the EDDIE team | 0.1
6 | Test pipeline on workbench | Move all the code modules and test it on workbench | 2
7 | EDNA toll gate ingestion - Rep level data | Submit ticket for EDnA tollgate ingestion team for creation of D0 table for new input data | 1
8 | EDnA Consumption ticket | Submit ticket for EDnA tollgate consumption team for creation of VI2 table for new input data | 1
9 | Ticket for MFT Process | Submit ticket for MFT process in order to perform monthly refresh of new input data from network shared path | 1
10 | MFT testing | Ingestion team to test the MFT process in Dev for new input data | 4
11 | Push sales rep data to edna-pr | VI2 for new input data to be migrated to stage environment | 2
12 | CR for data | Update CR for new input data for migration to production | 3
13 | Push sales rep data to edna-pr | Ingestion team to push the new input data to production | 1
14 | EDnA Tollgate consumption for creation of VW, VI2 | EDDIE team to provide empty D2, VI2 and VW datasets for output data | 2
15 | Service account acces to both inputs inside edna-data-pr | Raise service now ticket for EDDIE use case (Dev) Google service account for input data read access in edna-data-pr | 3
16 | Check VW access | Validate the read access for the EDDIE use case in edna-data-pr | 1
17 | Update config file | Update input data sources must read from edna-data-pr | 1
18 | Validation of Modules | Manual validation of MLOps pipeline within workbench (pilot run with all input data from edan-data-pr) | 1
19 | Dockerization of image and create requirements.txt | Create a docker file and manually push the image to harbor | 1
20 | Trigger Pipeline | Trigger the pipeline from workbench using AIRFLOW template | 1
21 | Fix refactorized code for errors in development environment (Manual Trigger) | Debug if any errors occur | 1
22 | Vertex AI integration | EDDIE team to provide Nitro DX setup | 1
23 | Push codes to GitHub | Push refactored modules to "src" folder and AIRFLOW DAG to "DAG" folder respectively inside EDDIE use case GithHub repository | 0.2
24 | Vertex AI integration | Create Airflow DAG and upload to Airflow GCS bucket in EDDIE Dev environment | 1
25 | AIRFLOW DAG TO EDDIE | Trigger the entire Nitro DX pipeline using Airflow DAG | 1

## Stage
S.No | Activity | Description | Business Days To Complete
1 | Onboarding to stage | EDDIE team to onboard EDDIE usecase to stage | 1
2 | Service account access for Stage | Raise service now ticket for EDDIE use case (Stage) Google service account for input data read access in edna-data-pr | 1
3 | Integration on stage environment | Push the updated code to GitHub for Stage | 0.1
4 | Integration on stage environment | Modify Config.yaml, Set up AIRFLOW DAG for Stage | 0.5
5 | Migrate AIRFLOW DAG to Stage | Jira card approval from EDDIE team to migrate AIRFLOW DAG from Dev to Stage | 0.1
6 | Integration on stage environment | Ensure code is running without issues in MLOps Stage pipeline and debug for errors | 1
7 | Documents for active CR | Testing documents, T Minus document, Approval email from Business | 1
8 | CR Review | Attach Testing documents, T Minus document and Approval email from Business and Get CR Approved from the Board | 0.1

## Prod
S.No | Activity | Description | Business Days To Complete
1 | Onboarding to production | EDDIE team to onboard EDDIE usecase to production | 1
2 | Service account access for production | Raise service now ticket for EDDIE use case (Production) Google service account for input data read access in edna-data-pr | 1
3 | Integration on production environment | Push the updated code to GitHub for production | 0.1
4 | Integration on production environment | Modify Config.yaml, Set up AIRFLOW DAG for production | 0.5
5 | Migrate AIRFLOW DAG from Dev to Stage | Additional Jira card approval by EDDIE team migrate AIRFLOW DAG from Dev to Stage as production environment ingests AIRFLOW DAG directly from Stage and not from GitHub | 0.1
6 | Migrate AIRFLOW DAG from Stage to Prod | Jira card approval from EDDIE team to migrate AIRFLOW DAG from Stage to production | 0.1
7 | Integration on production environment | Ensure code is running without issues in MLOps production pipeline and debug for errors | 1